## Overview
WebEngage Custom Agents — Clarification Overview
A stakeholder decision workbook for the proposed Java / Spring Boot custom-agent platform
Total questions |  | Blocking decisions |  | Decided |  | Completion
72 |  | 38 |  | 72 |  | 100%
Working agreement: resolve all blocking questions, record one accountable owner, and mark a row Decided only after stakeholder approval. Recommended defaults are implementation assumptions—not silent decisions.
Decision progress by theme
Theme | Total | Critical | Blocking | Decided | Open | Progress
Custom-agent programming model | 6 | 3 | 3 | 6 | 0 | 100%
Core Agentic Layer | 7 | 4 | 4 | 7 | 0 | 100%
WebEngage tools | 7 | 3 | 3 | 7 | 0 | 100%
Agent and execution APIs | 6 | 2 | 2 | 6 | 0 | 100%
Scheduling | 6 | 5 | 5 | 6 | 0 | 100%
Authentication and authorization | 8 | 7 | 7 | 8 | 0 | 100%
Conversation and audit logging | 8 | 5 | 5 | 8 | 0 | 100%
Persistence and infrastructure | 6 | 5 | 5 | 6 | 0 | 100%
Technology choices | 5 | 1 | 1 | 5 | 0 | 100%
Reliability and operations | 7 | 2 | 2 | 7 | 0 | 100%
Delivery scope | 6 | 1 | 1 | 6 | 0 | 100%
How to use this workbook
1. Filter the Questions tab by Primary stakeholder and Blocking?. 2. Enter a concrete response, decision owner, and due date. 3. Use In Review while validating and Blocked only when a named dependency exists. 4. Change Status to Decided after approval. 5. Review this Overview tab until all Blocking decisions are resolved.

## Questions
WebEngage Custom Agents — Stakeholder Clarification Tracker
Complete all Critical / Blocking questions before implementation. Yellow columns are stakeholder-owned inputs.
Generated 31 Jul 2026 • 72 questions • Update one accountable decision owner per row
ID | Theme | Clarifying question | Decision / recommended default | Primary stakeholder | Supporting stakeholders | Priority | Blocking? | Why it matters | Response / decision | Decision owner | Status | Due date | Notes / follow-up
Q01 | Custom-agent programming model | When users ‘write their own agents,’ what artifact will they provide? | Choose one: declarative definition; Java source upload; compiled JAR/plugin; or Java classes deployed with this service. Recommended: declarative definitions with trusted Java tool components. | Product | Platform Architecture; Security / IAM; Backend Engineering | Critical | Yes | The choice determines deployment, isolation, security, and lifecycle architecture. | Declarative definitions like role play, instruction/Rules, output format, other context inputs like extternal file etc. Trusted tools selected from the pre defined webengage tools. | Product Team | Decided
Q02 | Custom-agent programming model | Must new or updated agents become available without rebuilding or restarting the service? | Recommended: yes for declarative definitions; controlled deployment for trusted Java extensions. | Product | Platform Architecture; SRE / Infrastructure | High | No | Clarifies whether runtime registration and hot reload are required. | Yes, as all the agent related information is stored in DB, the code should use that info to spawn an agent | Engineering | Decided
Q03 | Custom-agent programming model | Do agents require draft, published, and versioned states, or should every update become active immediately? | Recommended: Draft → Published → Retired with immutable published versions. | Product | Backend Engineering; Data Privacy / Compliance | High | No | Defines safe authoring, rollback, and audit behavior. | Yes, Draft → Published → Retired with immutable published versions. |  | Decided
Q04 | Custom-agent programming model | Can an agent invoke any registered tool, or only an explicit per-agent allowlist? | Recommended: explicit allowlist, validated at publish and run time. | Security / IAM | Product; Core Platform / Tool Owners | Critical | Yes | Controls privilege boundaries and limits unintended actions. | Allowed list for now |  | Decided
Q05 | Custom-agent programming model | Should each agent define an input and output JSON Schema? | Recommended: yes; require input schema and allow optional output schema. | Product | Platform Architecture; Backend Engineering | High | No | Enables validation, discoverability, and stable API contracts. | The input schema should be prepared using the information provided at the time of agent creation. The user should be able to define their own input sections. Also provision to provide few examples too at the time of agent creation. Output schema can be asked at the time of agent creation. Will iterate on the output |  | Decided
Q06 | Custom-agent programming model | Can agents store configuration or secrets, and how should secrets be represented? | Recommended: store non-secret configuration; reference secrets by vault identifier only. | Security / IAM | SRE / Infrastructure; Backend Engineering | Critical | Yes | Prevents credentials from leaking into definitions and transcripts. | No, Can refer to the Vault secrets. |  | Decided
Q07 | Core Agentic Layer | What is the Core Agentic Layer endpoint, HTTP method, and request/response contract? | Provide OpenAPI or representative request/response examples, including errors. | Core Agentic Layer | Platform Architecture; Backend Engineering | Critical | Yes | The orchestration client cannot be implemented without a stable contract. | Not yet defined but open for suggestions, The Input/output can follow the OpenAI contract. |  | Decided
Q08 | Core Agentic Layer | Is the tool-calling protocol OpenAI-compatible or WebEngage-specific? | Recommended: document a versioned internal contract even if it mirrors OpenAI tool calling. | Core Agentic Layer | Platform Architecture | Critical | Yes | Determines message types, tool-call parsing, and compatibility strategy. | webengage specific MCPs |  | Decided
Q09 | Core Agentic Layer | Should this service perform the full agent loop: send context, receive tool calls, execute tools, return results, and repeat until a final answer? | Recommended: yes; the custom-agent service owns tool execution and the Core Agentic Layer owns model generation. | Platform Architecture | Core Agentic Layer; Core Platform / Tool Owners | Critical | Yes | Establishes the service boundary and orchestration responsibility. | yes; the custom-agent service owns tool execution and the Core Agentic Layer owns model generation. |  | Decided
Q10 | Core Agentic Layer | What maximum iterations, wall-clock timeout, token limit, and cost limit should apply per execution? | Recommended starting point: 10 iterations, 5-minute timeout, configurable token/cost ceilings. | Product | Core Agentic Layer; SRE / Infrastructure | Critical | Yes | Prevents runaway loops and unbounded latency or spend. | starting point: 10 iterations, 5-minute timeout, configurable token/cost ceilings. Should be configurable as needed |  | Decided
Q11 | Core Agentic Layer | Should multiple tool calls returned in one model response execute in parallel? | Recommended: parallel only for tools declared read-only and concurrency-safe. | Platform Architecture | Core Platform / Tool Owners; Backend Engineering | High | No | Affects performance, ordering, and side-effect safety. | parallel only for tools declared read-only and concurrency-safe. |  | Decided
Q12 | Core Agentic Layer | Should conversation context persist across separate executions or only within one run? | Recommended: isolate by run initially; add explicit conversation/session IDs if cross-run continuity is needed. | Product | Data Privacy / Compliance; Platform Architecture | High | No | Determines storage model, privacy scope, and context assembly. | isolate by run initially; add explicit conversation/session IDs if cross-run continuity is needed. |  | Decided
Q13 | Core Agentic Layer | Is a mock Core Agentic Layer acceptable for local development and automated tests? | Recommended: yes, with deterministic scripted tool-call scenarios. | QA / Release Engineering | Core Agentic Layer; Backend Engineering | Medium | No | Enables reliable development and integration testing without model dependency. | yes, with deterministic scripted tool-call scenarios. |  | Decided
Q14 | WebEngage tools | What are the initial tools and their request/response contracts? | Provide tool names, descriptions, JSON schemas, owners, side-effect classification, and examples. | Core Platform / Tool Owners | Product; Platform Architecture | Critical | Yes | Tool definitions are foundational inputs to agent configuration and execution. | Open, will add a doc for the same. suggest em a doc format to declare the tolls |  | Decided
Q15 | WebEngage tools | How are core-platform tools exposed: HTTP, gRPC, Kafka, Java SDKs, or a combination? | Document the protocol and service endpoint for each initial tool. | Core Platform / Tool Owners | Platform Architecture; Backend Engineering | Critical | Yes | Drives connector abstractions, error handling, and deployment dependencies. | Will document in the same tool doc |  | Decided
Q16 | WebEngage tools | How should this service authenticate to core platforms: service credentials, delegated user identity, or both? | Recommended: service identity plus delegated user/account context where authorization requires it. | Security / IAM | Core Platform / Tool Owners; Platform Architecture | Critical | Yes | Defines downstream trust and least-privilege enforcement. | A service account token will be used for oAuth for all tool calls |  | Decided
Q17 | WebEngage tools | Are tools synchronous, asynchronous, or mixed? | Classify every initial tool and define polling or callback behavior for asynchronous tools. | Core Platform / Tool Owners | Backend Engineering; SRE / Infrastructure | High | No | Determines orchestration state transitions and execution persistence. | Can be both sync/async. I case of async willl tool will define a placeholder to provide a call back method |  | Decided
Q18 | WebEngage tools | Should failed tool calls be retried, and which operations are safe to retry? | Recommended: retry only idempotent operations; require idempotency keys for retryable writes. | Core Platform / Tool Owners | Platform Architecture; SRE / Infrastructure | High | No | Avoids duplicate side effects while improving resilience. | retry only idempotent operations; require idempotency keys for retryable writes. |  | Decided
Q19 | WebEngage tools | Do sensitive or high-impact tools require human confirmation or approval before execution? | Recommended: risk-tier tools and require approval for destructive, external, or high-volume actions. | Security / IAM | Product; Core Platform / Tool Owners; Data Privacy / Compliance | High | No | Establishes guardrails for consequential actions. | risk-tier tools and require approval for destructive, external, or high-volume actions. |  | Decided
Q20 | WebEngage tools | Should the framework expose a standard Java tool interface and registry for tools implemented as Spring beans? | Recommended: yes, with metadata, input schema, authorization hook, execution method, and result schema. | Platform Architecture | Backend Engineering; Core Platform / Tool Owners | High | No | Creates a consistent extension model and test surface. | yes, with metadata, input schema, authorization hook, execution method, and result schema. Should be implemented using the tools definition defined in a doc |  | Decided
Q21 | Agent and execution APIs | Which API capabilities are required in the first release? | Confirm: agent CRUD/list; publish/version; run; status/result; cancel; run/transcript history; schedule CRUD and enable/disable. | Product | Backend Engineering; Platform Architecture | Critical | Yes | Fixes the external API scope and delivery boundary. | start with agent CRUD/list and execution by an api call to test the agent |  | Decided
Q22 | Agent and execution APIs | Should execution be synchronous, asynchronous, or both? | Recommended: both; asynchronous by default and synchronous with a strict timeout. | Product | Platform Architecture; SRE / Infrastructure | Critical | Yes | Determines response semantics, persistence, and worker design. | both; asynchronous by default and synchronous with a strict timeout. |  | Decided
Q23 | Agent and execution APIs | What should an execution trigger contain besides agent ID? | Confirm arbitrary JSON input, user context, account/license identifier, correlation ID, and idempotency key. | Product | Security / IAM; Backend Engineering | High | No | Defines validation, tenancy, tracing, and replay protection. | Just an agent ID to start with but can be enhanced |  | Decided
Q24 | Agent and execution APIs | Should deleted agents be soft-deleted for auditability? | Recommended: soft delete, with admin-only purge subject to retention policy. | Data Privacy / Compliance | Product; Backend Engineering | High | No | Balances audit requirements with eventual data deletion. | Soft deleted |  | Decided
Q25 | Agent and execution APIs | What pagination, sorting, and filtering conventions should the REST APIs follow? | Provide WebEngage standards; otherwise use cursor pagination for runs and page/size for agent administration. | Backend Engineering | Product; Platform Architecture | Medium | No | Keeps APIs consistent and scalable. | standard |  | Decided
Q26 | Agent and execution APIs | Is REST with OpenAPI/Swagger sufficient, or is another API style required? | Recommended: versioned REST JSON APIs documented with OpenAPI 3.1. | Platform Architecture | Product; Backend Engineering | High | No | Sets the interface standard and documentation approach. | versioned REST JSON APIs documented with OpenAPI 3.1. |  | Decided
Q27 | Scheduling | Should schedules accept cron expressions, fixed intervals, or both? | Recommended: both, normalized internally to a schedule definition. | Product | Backend Engineering | Critical | Yes | Defines scheduling API and validation behavior. | both, normalized internally to a schedule definition. |  | Decided
Q28 | Scheduling | Which timezone should schedules use: per schedule, account timezone, or UTC? | Recommended: IANA timezone per schedule, defaulting to account timezone, with UTC storage. | Product | SRE / Infrastructure; Backend Engineering | Critical | Yes | Prevents ambiguous trigger times and daylight-saving errors. | IANA timezone per schedule, defaulting to account timezone, with UTC storage. |  | Decided
Q29 | Scheduling | What should happen if a scheduled run is active when the next occurrence arrives? | Choose per schedule: Skip, Queue, or Parallel. Recommended default: Skip. | Product | SRE / Infrastructure; Platform Architecture | Critical | Yes | Controls duplicate work and execution backlog. | Skip if already running, will rovision for queue later |  | Decided
Q30 | Scheduling | What should happen to missed executions after downtime? | Choose Skip or Catch up. Recommended default: skip and record a misfire event. | Product | SRE / Infrastructure | Critical | Yes | Defines predictable recovery after outages. | Skip |  | Decided
Q31 | Scheduling | Will the service run with multiple replicas, and may it use a clustered scheduler backed by PostgreSQL? | Recommended: yes; use clustered Quartz or an approved existing job platform. | SRE / Infrastructure | Platform Architecture; Backend Engineering | Critical | Yes | Avoids duplicate firing and ensures high-availability scheduling. | Existing scheduler, will specify the api contract |  | Decided
Q32 | Scheduling | Do schedules need start/end dates and a maximum execution count? | Recommended: optional start/end dates; optional maximum run count. | Product | Backend Engineering | High | No | Supports bounded campaigns and operational control. | optional start/end dates; optional maximum run count. |  | Decided
Q33 | Authentication and authorization | Which identity provider and token format should the service support? | Provide OIDC/OAuth2 details. Recommended: Spring Security resource server validating JWTs. | Security / IAM | Platform Architecture; Backend Engineering | Critical | Yes | Authentication cannot be implemented safely without the trust source. | Not auth to start with |  | Decided
Q34 | Authentication and authorization | What JWT issuer, audience, and role/identity claim names should be validated? | Provide values or confirm configurable placeholders for local environments. | Security / IAM | Backend Engineering | Critical | Yes | Defines token validation and identity extraction. | Skip to start with |  | Decided
Q35 | Authentication and authorization | What roles and permissions are required? | Proposed roles: AGENT_VIEWER, AGENT_AUTHOR, AGENT_OPERATOR, AGENT_ADMIN; confirm permission matrix. | Security / IAM | Product; Data Privacy / Compliance | Critical | Yes | Creates the authorization model for each endpoint and action. | Skip to start with |  | Decided
Q36 | Authentication and authorization | Are agents private to creators, shared within a team/account, or globally visible? | Recommended: account-scoped by default, with explicit owner and sharing metadata. | Product | Security / IAM; Data Privacy / Compliance | Critical | Yes | Defines data visibility and access checks. | account-scoped by default, with explicit owner and sharing metadata. |  | Decided
Q37 | Authentication and authorization | Is the system multi-tenant, and which identifier establishes the tenant boundary? | Confirm WebEngage account, license code, workspace, or another immutable claim. | Security / IAM | Product; Platform Architecture | Critical | Yes | Tenant isolation must be embedded in every query and execution. | WebEngage license code |  | Decided
Q38 | Authentication and authorization | Can administrators read execution transcripts belonging to other users or tenants? | Recommended: tenant admins may read their tenant only; cross-tenant access requires an audited support role. | Data Privacy / Compliance | Security / IAM; Product | Critical | Yes | Transcripts can contain sensitive customer and platform data. | tenant admins may read their tenant only |  | Decided
Q39 | Authentication and authorization | Should the initiating user’s identity and permissions be revalidated when a scheduled job runs later? | Recommended: validate the schedule owner and current permissions at execution time; define service-owner fallback explicitly. | Security / IAM | Product; SRE / Infrastructure | Critical | Yes | Prevents schedules from retaining revoked privileges indefinitely. | Skip to start with |  | Decided
Q40 | Authentication and authorization | Is service-to-service authentication required in addition to human-user authentication? | Recommended: yes; use workload identity or signed service tokens for internal callers. | Security / IAM | SRE / Infrastructure; Platform Architecture | High | No | Supports API-triggered automation without impersonating a person. | service to service basic auth |  | Decided
Q41 | Conversation and audit logging | Where should per-run transcripts be stored? | Recommended: PostgreSQL for searchable metadata and messages initially; external object storage for oversized payloads if needed. | Platform Architecture | Data Privacy / Compliance; SRE / Infrastructure | Critical | Yes | Storage choice shapes consistency, search, retention, and scale. | MySQL for searchable metadata and messages initially; external object storage for oversized payloads if needed. |  | Decided
Q42 | Conversation and audit logging | Which run events must be recorded? | Confirm trigger input, prompts, model responses, tool requests/results, retries/errors, final output, timing, and token usage. | Product | Data Privacy / Compliance; Core Agentic Layer; Backend Engineering | Critical | Yes | Defines the authoritative execution history and debugging evidence. | skip to start with |  | Decided
Q43 | Conversation and audit logging | May raw prompts and tool results be retained, or must sensitive fields be redacted or encrypted? | Recommended: classify fields; redact credentials; encrypt sensitive payloads; allow tool-specific redaction policies. | Data Privacy / Compliance | Security / IAM; Core Platform / Tool Owners | Critical | Yes | Prevents the log from becoming a sensitive-data liability. | skip to start with |  | Decided
Q44 | Conversation and audit logging | What retention period applies to transcripts and audit events? | Specify separate retention for execution content and immutable audit metadata. | Data Privacy / Compliance | Product; SRE / Infrastructure | Critical | Yes | Controls storage sizing and compliance with deletion obligations. | skip to start with |  | Decided
Q45 | Conversation and audit logging | Should transcript access require a separate permission? | Recommended: yes, separate VIEW_AGENT_TRANSCRIPT from VIEW_AGENT and RUN_AGENT. | Security / IAM | Data Privacy / Compliance; Product | High | No | Agent metadata is generally less sensitive than execution content. | skip to start with |  | Decided
Q46 | Conversation and audit logging | Do stakeholders need searchable transcripts and a transcript retrieval API? | Recommended: filter by tenant, agent, run, status, initiator, and time range; avoid full-text search in the MVP unless required. | Product | Backend Engineering; Data Privacy / Compliance | High | No | Determines indexing and API scope. | skip to start with |  | Decided
Q47 | Conversation and audit logging | Are there compliance requirements for PII, data residency, encryption, legal hold, or deletion? | Provide applicable policies and approved storage regions/services. | Data Privacy / Compliance | Security / IAM; SRE / Infrastructure | Critical | Yes | May materially constrain architecture and operational procedures. | skip to start with |  | Decided
Q48 | Conversation and audit logging | Should CRUD, publishing, scheduling, and manual-run actions have immutable audit records? | Recommended: yes, including actor, tenant, action, target, timestamp, correlation ID, and before/after summary. | Data Privacy / Compliance | Security / IAM; Backend Engineering | High | No | Supports governance, investigations, and accountability. | skip to start with |  | Decided
Q49 | Persistence and infrastructure | Which database should the service target? | Recommended: PostgreSQL with Flyway migrations. | SRE / Infrastructure | Platform Architecture; Backend Engineering | Critical | Yes | Determines persistence implementation and operational ownership. | MySQL |  | Decided
Q50 | Persistence and infrastructure | Are Redis, Kafka, or another queue/job platform already available? | List approved shared infrastructure and usage constraints. | SRE / Infrastructure | Platform Architecture | Critical | Yes | Avoids inventing infrastructure and guides asynchronous execution design. | skip to start with |  | Decided
Q51 | Persistence and infrastructure | For asynchronous runs, should the service use an existing job platform, Kafka, or a database-backed worker? | Recommended: approved enterprise job/queue platform; otherwise transactional database-backed outbox and workers for the first release. | Platform Architecture | SRE / Infrastructure; Backend Engineering | Critical | Yes | Defines delivery guarantees, recovery, and scaling. | skip to start with |  | Decided
Q52 | Persistence and infrastructure | What is the deployment target: Kubernetes, VMs, or another environment? | Recommended: Kubernetes if it is the internal standard. | SRE / Infrastructure | Platform Architecture | Critical | Yes | Determines packaging, health checks, scaling, and configuration. | Kubernetes |  | Decided
Q53 | Persistence and infrastructure | Should delivery include Dockerfile, local Compose dependencies, health/readiness endpoints, and Kubernetes manifests? | Recommended: Dockerfile, local Compose, and Actuator probes; include manifests only if deployment conventions are provided. | SRE / Infrastructure | QA / Release Engineering; Backend Engineering | High | No | Defines the deployable artifact and local developer experience. | skip to start with |  | Decided
Q54 | Persistence and infrastructure | Are there internal WebEngage libraries, parent POMs, API standards, or artifact repositories that must be used? | Provide references and version constraints before scaffolding. | Platform Architecture | Backend Engineering; QA / Release Engineering | Critical | Yes | Ensures the project fits internal engineering and supply-chain standards. | skip to start with |  | Decided
Q55 | Technology choices | Are Java 21, Spring Boot 3.x, Spring Security, Spring Data JPA, PostgreSQL, Flyway, Quartz, and springdoc-openapi acceptable? | Recommended: yes, subject to WebEngage-supported versions and scheduler decision. | Platform Architecture | Backend Engineering; SRE / Infrastructure | Critical | Yes | Locks the baseline stack and compatibility envelope. | yes |  | Decided
Q56 | Technology choices | Should the project use Maven or Gradle? | Recommended: Maven unless WebEngage standardizes on Gradle. | Backend Engineering | Platform Architecture | High | No | Determines build, dependency, and CI conventions. | Maven |  | Decided
Q57 | Technology choices | What Java group/package name should be used? | Proposed: com.webengage.customagents. | Backend Engineering | Platform Architecture | Medium | No | Establishes stable namespace and artifact coordinates. | com.webengage.customagents. |  | Decided
Q58 | Technology choices | Should the project use Lombok, Java records/manual code, or another convention? | Recommended: records for immutable API DTOs; explicit entities; avoid Lombok unless it is an internal standard. | Backend Engineering | QA / Release Engineering | Medium | No | Keeps generated code aligned with maintainability conventions. | records for immutable API DTOs; explicit entities; avoid Lombok unless it is an internal standard. |  | Decided
Q59 | Technology choices | Is there a standard API response/error envelope and structured logging format to follow? | Provide examples; otherwise use RFC 9457 Problem Details and structured JSON logs. | Platform Architecture | Backend Engineering; SRE / Infrastructure | High | No | Ensures consistency with internal clients and operations. | use RFC 9457 Problem Details and structured JSON logs. |  | Decided
Q60 | Reliability and operations | What peak concurrent executions, schedule count, and API traffic should the system support? | Provide expected, peak, and first-year growth estimates. | Product | SRE / Infrastructure; Platform Architecture | Critical | Yes | Capacity assumptions affect queueing, database, and concurrency design. | Details not available |  | Decided
Q61 | Reliability and operations | What rate limits are required per user, tenant, agent, or tool? | Recommended: configurable tenant and tool limits, with stricter limits on costly or mutating tools. | Product | Security / IAM; SRE / Infrastructure | High | No | Protects shared services from abuse and noisy neighbors. | Details not available |  | Decided
Q62 | Reliability and operations | What availability target and maximum execution duration are required? | Provide SLOs; recommended initial maximum run duration is configurable with a hard cap. | SRE / Infrastructure | Product; Platform Architecture | Critical | Yes | Defines resilience, timeout, and operational investment. | Details not available |  | Decided
Q63 | Reliability and operations | Should an execution survive service restarts and resume from its last completed step? | Recommended: persist each orchestration step and resume safely for asynchronous runs. | Platform Architecture | SRE / Infrastructure; Backend Engineering | High | No | Determines durability and state-machine complexity. | skip to start with |  | Decided
Q64 | Reliability and operations | What retry, backoff, and circuit-breaker behavior is expected for the Core Agentic Layer? | Recommended: bounded exponential backoff for transient failures, circuit breaker, and no retry for validation errors. | SRE / Infrastructure | Core Agentic Layer; Platform Architecture | High | No | Prevents cascading failures and improves controlled recovery. | skip to start with |  | Decided
Q65 | Reliability and operations | Which observability stack should be integrated? | Confirm Micrometer/Prometheus, OpenTelemetry, Datadog, or internal equivalents. | SRE / Infrastructure | Backend Engineering | High | No | Determines metrics, trace, log, and dashboard integrations. | skip to start with |  | Decided
Q66 | Reliability and operations | Should token usage, model latency, tool latency, success rate, and estimated cost be recorded? | Recommended: yes, tagged by tenant and agent with privacy-safe cardinality controls. | Product | Core Agentic Layer; SRE / Infrastructure; Data Privacy / Compliance | High | No | Enables cost governance, performance tuning, and service reporting. | yes, tagged by tenant and agent with privacy-safe cardinality controls. |  | Decided
Q67 | Delivery scope | Should the first delivery be a production-oriented foundation or a smaller MVP? | Recommended: production-oriented vertical slice with a limited initial tool set. | Product | Platform Architecture; Backend Engineering | Critical | Yes | Aligns implementation depth, timeline, and acceptance criteria. | MVP |  | Decided
Q68 | Delivery scope | Which automated test levels are required? | Recommended: unit, Spring integration, Testcontainers database, authorization, scheduler, and deterministic agent-loop tests. | QA / Release Engineering | Backend Engineering; Security / IAM | High | No | Defines quality gates and delivery effort. | Skip to start with |  | Decided
Q69 | Delivery scope | Is generated OpenAPI documentation sufficient, or are architecture and operational documents also required? | Recommended: OpenAPI plus architecture overview, data model, runbook, and extension guide. | Platform Architecture | Product; SRE / Infrastructure | High | No | Ensures the service can be adopted and operated by other teams. | OpenAPI is sufficient |  | Decided
Q70 | Delivery scope | Should the repository include sample agents and tools demonstrating the complete tool-calling loop? | Recommended: yes, one read-only example and one guarded mutating example. | Product | Backend Engineering; QA / Release Engineering | High | No | Provides an executable reference for future agent and tool authors. | yes, one read-only example and one guarded mutating example. |  | Decided
Q71 | Delivery scope | Is CI configuration required, and which platform should it target? | Provide the approved platform and required checks; recommended checks include build, tests, lint, dependency scan, and image scan. | QA / Release Engineering | SRE / Infrastructure; Security / IAM | High | No | Defines repeatable delivery and security gates. | Skip to start with |  | Decided
Q72 | Delivery scope | Should backward-compatible API/database evolution and optimistic locking be included in the first version? | Recommended: versioned migrations and optimistic locking from the outset; API compatibility rules documented. | Platform Architecture | Backend Engineering; Product | High | No | Reduces lost updates and unsafe future evolution. | Skip to start with |  | Decided

## Stakeholder Routing
Stakeholder Routing & Review Responsibilities
Use this tab to distribute the Questions tab to the right decision-makers and track their review load.
Stakeholder | Primary focus | Input expected | Primary questions | Blocking questions | Suggested accountable role
Product | Product scope, behavior, sharing model, and acceptance criteria | Choose business defaults and approve the first-release boundary | 22 | 12 | Product Manager / Agent Platform Owner
Platform Architecture | Service boundaries, runtime model, contracts, and extensibility | Approve architecture decisions and internal platform alignment | 12 | 5 | Principal / Staff Architect
Core Agentic Layer | LLM-generation API, tool-calling protocol, limits, and errors | Supply a versioned contract, examples, and test endpoint or mock | 2 | 2 | Core Agentic Layer Tech Lead
Core Platform / Tool Owners | Tool schemas, side effects, reliability, and downstream APIs | Document and approve every initial tool contract | 4 | 2 | Owning Platform Tech Lead(s)
Security / IAM | Identity, authorization, secrets, delegated access, and approvals | Approve trust boundaries, claims, roles, and sensitive-action controls | 11 | 8 | Security Architect / IAM Owner
Data Privacy / Compliance | Retention, PII, audit, encryption, residency, and deletion | Define policy constraints and approve transcript/audit handling | 6 | 4 | Privacy / Compliance Owner
SRE / Infrastructure | Deployment, persistence, scheduling, scaling, and observability | Confirm supported infrastructure, SLOs, and operational standards | 8 | 5 | SRE / Infrastructure Lead
Backend Engineering | Java/Spring implementation standards and API conventions | Confirm engineering standards and feasibility of proposed defaults | 4 | 0 | Backend Engineering Lead
QA / Release Engineering | Test strategy, CI, release gates, and local testability | Approve test strategy and delivery pipeline requirements | 3 | 0 | QA / Release Lead
Suggested review sequence
1. Product + Architecture resolve the programming model, service boundary, and release scope. 2. Core Agentic Layer + Tool Owners provide executable contracts. 3. Security + Privacy approve identity, tool permissions, transcripts, and retention. 4. SRE confirms persistence, scheduling, deployment, capacity, and observability. 5. Engineering + QA finalize implementation conventions and delivery gates.

## Reference
Reference & Response Guidance
Use these definitions to keep stakeholder responses consistent and decision-ready.
Status | Definition | Priority | Definition | Blocking? | Definition | Stakeholder | Primary review focus
Not Started | No stakeholder input has been recorded. | Critical | Required before architecture or implementation can safely proceed. | Yes | Implementation should not begin without a decision. | Product | Product scope, behavior, sharing model, and acceptance criteria
In Review | Input is being discussed or requires validation. | High | Materially affects the first release design or scope. | No | A recommended default can be used temporarily. | Platform Architecture | Service boundaries, runtime model, contracts, and extensibility
Blocked | A dependency prevents a decision. | Medium | Can use a documented default if stakeholders do not override it. |  |  | Core Agentic Layer | LLM-generation API, tool-calling protocol, limits, and errors
Decided | A decision is approved and ready for implementation. |  |  |  |  | Core Platform / Tool Owners | Tool schemas, side effects, reliability, and downstream APIs
[6 empty] | Security / IAM | Identity, authorization, secrets, delegated access, and approvals
Response standard | [5 empty] | Data Privacy / Compliance | Retention, PII, audit, encryption, residency, and deletion
For every decision, record the chosen option or concrete requirement in ‘Response / decision’, name a single accountable decision owner, update Status to Decided only after approval, and use Notes / follow-up for dependencies or action items. If the recommended default is accepted, state ‘Accept recommended default’ explicitly. | [5 empty] | SRE / Infrastructure | Deployment, persistence, scheduling, scaling, and observability
[6 empty] | Backend Engineering | Java/Spring implementation standards and API conventions
[6 empty] | QA / Release Engineering | Test strategy, CI, release gates, and local testability